## Main Data
[22 empty] | Jangan Diisi |  |  | Jangan Diisi |  |  | Jangan Diisi | Jangan Diisi |  | Jangan Diisi | Jangan Diisi |  |  | Jangan Diisi | Jangan Diisi |  |  |  | Jangan Diisi
No. | KKKS | Wilayah Kerja | Asset | Field | Nama Sumur | C/F, C/O, New | Jenis Pekerjaan | Kategori Sumur | Tipe Sumur | Status Sumur | Nama Rig | Tipe Rig | HP Rig | WP&B 2022 | Plan - Durasi Operasi (days) | Plan - Depth (mMD) | AFE Budget | Longitude | Latitude | Actual - Start Move Date | Actual - Finish Move Date | Actual - Move (days) | Actual - Start R/U Endurance Date | Actual - Finish R/U Endurance Date | Actual - R/U Endurance (days) | Actual - Start Drilling Date | Actual - Finish Drilling Date | Actual - Drilling (days) | Actual - Start Completion Date | Actual - Finish Completion Date | Actual - Completion (days) | Actual - Operation (days) | Actual - Start R/D Date | Actual - Finish R/D Date | Actual - R/D (days) | Actual - Total | Actual - Depth (mMD) | Actual - DHB Cost | Actual - CHB Cost | Actual - Total Cost
1 | P | Indonesia | Zone F | J | J1 | C/F | New Well | Development | Directional |  | P#42.3 | Rig Darat | 1000 | 2022-06-22 | 39 | 1997 | 3640285 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
2 | P | Indonesia | Zone F | J | J2 | C/F | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-02-15 | 20.2 | 1572 | 2868237 |  |  | 2022-02-02 | 2022-02-05 09:00 | 3.375 | 2022-02-05 09:00 | 2022-02-21 20:00 | 16.4583 | 2022-02-21 20:00 | 2022-03-04 20:00 | 11 | 2022-03-04 20:00 | 2022-03-20 | 15.1667 | 26.1667 | 2022-03-20 | 2022-03-22 12:00 | 2.5 | 48.5 | 1569 | 1485151.9541 | 915173.2597 | 2400325.2138
3 | P | Indonesia | Zone F | J | J3 | C/F | New Well | Development | Directional |  | P#17 | Rig Darat | 550 | 2022-09-02 | 33.4 | 1484 | 3072122 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
4 | P | Indonesia | Zone F | J | J4 | New | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-07-15 | 19.7 | 1157.7 | 2692554 |  |  | 2022-07-06 08:00 | 2022-07-12 08:00 | 6 | 2022-07-12 08:00 | 2022-08-05 06:00 | 23.9167 | 2022-08-05 06:00 | 2022-08-14 08:30 | 9.1042 | 2022-08-14 08:30 | 2022-08-24 16:00 | 10.3125 | 19.4167 | 2022-08-24 16:00 | 2022-08-27 | 2.3333 | 51.6667 | 1157.7 | 1281085.9424 | 783380.9122 | 2064466.8545
5 | P | Indonesia | Zone F | R | R1 | New | New Well | Development | Directional |  | T#12 | Rig Darat | 550 | 2022-05-15 | 38.5 | 1350 | 2983792 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
6 | P | Indonesia | Zone F | R | R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | 21.1 | 1300 | 2851130 | 98.0522 | 4.2896 | 2022-05-30 06:00 | 2022-06-02 15:00 | 3.375 | 2022-06-02 15:00 | 2022-06-14 18:00 | 12.125 | 2022-06-14 18:00 | 2022-07-06 13:00 | 21.7917 | 2022-07-06 13:00 | 2022-07-19 | 12.4583 | 34.25 | 2022-07-19 | 2022-07-22 | 3 | 52.75 | 1370 | 2084781.7294 | 1075906.8523 | 3160688.5817
7 | P | Indonesia | Zone F | R | R3 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-07-02 | 18.92 | 820 | 2766044.56 | 98.1062 | 4.334 | 2022-03-01 | 2022-04-25 07:00 | 55.2917 |  |  | 0 | 2022-04-25 07:00 | 2022-05-03 | 7.7083 | 2022-05-03 | 2022-05-18 | 15 | 22.7083 | 2022-05-18 | 2022-05-21 | 3 | 81 | 820 | 1630790.9985 | 735832.8372 | 2366623.8357
8 | P | Indonesia | Zone F | R | R4 | New | New Well | Development | Vertical |  | T#12 | Rig Darat | 550 | 2022-10-02 | 19.1 | 850 | 2227744 | 98.0992 | 4.3352 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
9 | P | Indonesia | Zone F | R | R5 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-08-02 | 22.5 | 790 | 2489280 | 98.0996 | 4.3376 | 2022-06-28 | 2022-06-30 16:00 | 2.6667 | 2022-07-01 | 2022-07-10 11:00 | 9.4583 | 2022-07-10 11:00 | 2022-07-18 | 7.5417 | 2022-07-18 | 2022-07-31 16:00 | 13.6667 | 21.2083 | 2022-07-31 16:00 | 2022-08-02 16:00 | 2 | 35.3333 | 790 | 1166626.3932 | 969960.3935 | 2136586.7867
10 | P | Indonesia | Zone F | R | R6 | New | New Well | Development | Vertical |  | P#23.1 | Rig Darat | 400 | 2022-11-15 | 21.6 | 750 | 3183371 | 98.1036 | 4.3372 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
11 | P | Indonesia | Zone F | R | R7 | New | New Well | Development | Vertical |  | P#23.1 | Rig Darat | 400 | 2022-09-15 | 21.5 | 720 | 2400606 | 98.1113 | 4.3419 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
12 | P | Indonesia | Zone F | R | R8 | C/F | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-01-02 | 21.77 | 800 | 2318089 | 98.1059 | 4.3365 | 2021-12-20 | 2021-12-24 | 4 | 2021-12-24 | 2022-01-01 | 8 | 2022-01-01 | 2022-01-09 22:00 | 8.9167 | 2022-01-09 22:00 | 2022-01-23 14:00 | 13.6667 | 22.5833 | 2022-01-23 14:00 | 2022-01-25 14:00 | 2 | 36.5833 | 802 | 1225106.9856 | 654625.2072 | 1879732.1928
13 | P | Indonesia | Zone F | R | R9 | New | New Well | Development | Vertical |  | P#23.1 | Rig Darat | 400 | 2022-08-15 | 36.9 | 804 | 2442750 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
14 | P | Indonesia | Zone F | R | R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | 22.5 | 780 | 2505645 | 98.1145 | 4.3361 |  |  | 0 |  |  | 0 | 2022-08-17 06:00 | 2022-08-31 10:00 | 14.1667 | 2022-08-31 10:00 | 2022-09-28 | 27.5833 | 41.75 |  |  | 0 | 41.75 | 780 | 1568197.6731 | 1325500.2863 | 2893697.9595
15 | P | Indonesia | Zone F | R | R11 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-03-15 | 17.1 | 715 | 2557831.42 | 98.1102 | 4.3471 | 2022-04-08 14:00 | 2022-04-11 14:00 | 3 | 2022-04-11 14:00 | 2022-04-23 05:00 | 11.625 | 2022-04-23 05:00 | 2022-04-30 05:00 | 7 | 2022-04-30 05:00 | 2022-05-10 06:00 | 10.0417 | 17.0417 | 2022-05-10 06:00 | 2022-05-12 06:00 | 2 | 33.6667 | 715 | 1631787.4111 | 693384.3642 | 2325171.7753
16 | P | Indonesia | Zone F | R | R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | 17.1 | 715 | 2213895 | 98.1074 | 4.3479 | 2022-05-12 15:00 | 2022-05-14 15:00 | 2 | 2022-05-14 15:00 | 2022-05-24 08:00 | 9.7083 | 2022-05-24 08:00 | 2022-05-31 18:30 | 7.4375 | 2022-05-31 18:30 | 2022-06-13 14:00 | 12.8125 | 20.25 | 2022-06-13 14:00 | 2022-06-15 14:00 | 2 | 33.9583 | 715.15 | 1652687.411 | 820461.735 | 2473149.1459
17 | P | Indonesia | Zone F | R | R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | 17.1 | 715 | 2254026 | 98.1023 | 4.351 | 2022-08-10 09:00 | 2022-08-12 09:00 | 2 | 2022-08-12 09:00 | 2022-08-21 10:00 | 9.0417 | 2022-08-21 10:00 | 2022-08-28 15:30 | 7.2292 | 2022-08-28 15:30 | 2022-09-06 21:00 | 9.2292 | 16.4583 | 2022-09-06 21:00 | 2022-09-08 21:00 | 2 | 29.5 | 715.1 | 1607042.1022 | 660540.522 | 2267582.6241
18 | P | Indonesia | Zone F | PS | PS1 | C/F | New Well | Development | Directional |  | P#41.3 | Rig Darat | 1000 | 2022-11-15 | 64.1 | 1920 | 6397170 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
19 | P | Indonesia | Zone F | J | J5 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-02-08 | 31.6 | 1804 | 3226593.01 |  |  | 2022-01-27 | 2022-01-31 | 4 | 2022-01-31 | 2022-02-09 18:00 | 9.75 | 2022-02-09 18:00 | 2022-02-21 01:00 | 11.2917 | 2022-02-21 01:00 | 2022-03-04 | 10.9583 | 22.25 | 2022-03-04 | 2022-03-07 | 3 | 39 | 1844 | 1622813.3722 | 917600.6188 | 2540413.991
20 | P | Indonesia | Zone F | J | J6 | C/O | New Well | Development | Directional |  | P#42.3 | Rig Darat | 1500 | 2022-05-02 | 43 | 2800 | 7626889.19 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
21 | P | Indonesia | Zone F | J | J7 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-03-22 | 29.2 | 1251 | 2508579 |  |  | 2022-03-07 06:00 | 2022-03-12 06:00 | 5 | 2022-03-12 06:00 | 2022-03-21 15:00 | 9.375 | 2022-03-21 15:00 | 2022-04-02 | 11.375 | 2022-04-02 | 2022-04-23 | 21 | 32.375 | 2022-04-23 | 2022-04-26 | 3 | 49.75 | 1251 | 1090648.2784 | 1165827.5916 | 2256475.8701
22 | P | Indonesia | Zone F | J | J8 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-06-08 | 27.8 | 1291 | 2362404 |  |  | 2022-05-14 06:00 | 2022-05-15 06:00 | 1 | 2022-05-15 06:00 | 2022-05-21 22:00 | 6.6667 | 2022-05-21 22:00 | 2022-05-30 11:00 | 8.5417 | 2022-05-30 11:00 | 2022-06-12 17:00 | 13.25 | 21.7917 | 2022-06-12 17:00 | 2022-06-15 17:00 | 3 | 32.4583 | 1286 | 848047.6475 | 1226303.9124 | 2074351.56
23 | P | Indonesia | Zone F | J | J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | 27.8333 | 1270.81 | 2433487 |  |  | 2022-07-17 06:00 | 2022-07-20 06:00 | 3 | 2022-07-20 06:00 | 2022-07-29 13:00 | 9.2917 | 2022-07-29 13:00 | 2022-08-07 14:00 | 9.0417 | 2022-08-07 14:00 | 2022-08-29 14:00 | 22 | 31.0417 | 2022-08-29 14:00 | 2022-09-01 14:00 | 3 | 46.3333 | 1275 | 1092510.742 | 1393160.4107 | 2485671.1526
24 | P | Indonesia | Zone F | J | J10 | New | New Well | Development | Directional | On Going | P#17 | Rig Darat | 550 | 2022-09-08 | 27.9 | 1307 | 2434078 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
25 | P | Indonesia | Zone F | J | J11 | C/O | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2021-12-22 | 24.7 | 1650 | 2623025.7528 |  |  | 2021-12-07 | 2021-12-11 09:00 | 4.375 | 2021-12-11 09:00 | 2021-12-25 | 13.625 | 2021-12-25 | 2022-01-09 15:30 | 15.6458 | 2022-01-09 15:30 | 2022-01-26 18:00 | 17.1042 | 32.75 | 2022-01-26 18:00 | 2022-01-28 18:00 | 2 | 52.75 | 1650 | 1540219.1055 | 887574.1634 | 2427793.2689
26 | P | Indonesia | Zone F | J | J12 | C/O | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2021-12-01 | 24.7 | 1211 | 2529742 |  |  | 2021-12-05 | 2021-12-17 | 12 | 2021-12-17 | 2021-12-23 21:00 | 6.875 | 2021-12-27 14:00 | 2022-01-03 19:30 | 7.2292 | 2022-01-03 19:30 | 2022-01-15 17:00 | 11.8958 | 19.125 | 2022-01-15 17:00 | 2022-01-18 17:00 | 3 | 41 | 1208 | 1262404.0252 | 814917.572 | 2077321.5971
27 | P | Indonesia | Zone F | J | J13 | New | New Well | Development | Directional | Completed | N#1 | Rig Darat | 550 |  | 31.6 | 1719.12 | 2466748 |  |  | 2022-05-06 08:00 | 2022-05-10 08:00 | 4 | 2022-05-10 08:00 | 2022-05-27 03:00 | 16.7917 | 2022-05-27 03:00 | 2022-06-09 13:00 | 13.4167 | 2022-06-09 13:00 | 2022-06-29 15:00 | 20.0833 | 33.5 | 2022-06-29 15:00 | 2022-07-01 15:00 | 2 | 56.2917 | 1743 | 973032.7108 | 1012638.2867 | 1985670.9976
28 | P | Indonesia | Zone F | J | J14 | C/O | New Well | Exploration | Directional | Completed | T#5 | Rig Darat | 700 | 2021-11-15 | 86.6 | 1919.39 | 10193828 |  |  | 2021-10-19 18:00 | 2021-11-05 18:00 | 17 |  |  | 0 | 2021-12-02 | 2021-12-24 04:00 | 22.1667 | 2021-12-24 04:00 | 2022-01-31 16:00 | 38.5 | 60.6667 | 2022-01-31 16:00 | 2022-02-03 17:00 | 3.0417 | 80.7083 | 1922 | 4059872.0076 | 3121542.125 | 7181414.1326
29 | P | Indonesia | Zone F | PB | PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | 213.83 | 4032.8 | 26620003 | 98.1867 | 3.9918 | 2021-03-03 | 2021-04-01 | 29 | 2021-04-02 10:00 | 2021-04-12 10:00 | 10 | 2021-04-12 10:00 | 2022-03-14 19:00 | 336.375 | 2022-03-14 19:00 | 2022-06-16 06:00 | 93.4583 | 429.8333 | 2022-06-16 06:00 | 2022-06-19 06:00 | 3 | 471.8333 | 3255 | 47485213.662 | 6400800.542 | 53886014.2041
30 | P | Indonesia | Zone F | J | J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | 62 | 2542.6416 | 11423390.2688 |  |  |  |  | 0 |  |  | 0 | 2022-03-07 18:00 | 2022-06-04 14:30 | 88.8542 | 2022-06-04 14:30 | 2022-09-08 | 95.3958 | 184.25 |  |  | 0 | 184.25 | 2190.1404 | 8477924.5155 | 13292152.3945 | 21770076.91
Formulas:
Jangan Diisi = MainData[[#This Row],[Actual - Finish Drilling Date]]

## Graph (hidden)
Field | (All)
Kategori Sumur | Development
Nama Rig | (All)
Row Labels | Plan Operation (days) | Actual Operation (days) | AFE Plan Budget | Total Actual Cost
Grand Total
|  | 2851130 | 3160688.5817 | -309558.5817
|  | 2318089 | 1879732.1928 | 438356.8072
|  | 2557831.42 | 2325171.7753 | 232659.6447
|  | 2766044.56 | 2366623.8357 | 399420.7243
|  | 2213895 | 2473149.1459 | -259254.1459
|  | 2489280 | 2136586.7867 | 352693.2133
|  | 2254026 | 2267582.6241 | -13556.6241

## Graph Center Gravity (hidden)
Field | (All)
Kategori Sumur | Development
Nama Rig | (All)
Row Labels | Sum of Delta Dur | Sum of Delta Cos | Row Labels | Sum of Delta Dur | Sum of Delta Cos | Plan Operation (days) | Actual Operation (days) | AFE Plan Budget | Total Actual Cost | TIME | COST
Grand Total | 0 | 0 | SGET-001 | 25.9333 | 3012413.8674 | 86.6 | 60.6667 | 10193828 | 7181414.1326 | 0.70054 | 0.70449
|  |  | CMA-001 | -244.2433 | -27266011.2041 | 185.59 | 429.8333 | 26620003 | 53886014.2041 | 2.316 | 2.0243
|  |  | SRT-1X | -122.25 | -10346686.6412 | 62 | 184.25 | 11423390.2688 | 21770076.91 | 2.9718 | 1.9057
|  |  | Ideal | [6 empty] | 0 | 0
[10 empty] | 100 | 100
|  |  | Row Labels | Sum of Delta Dur | Sum of Delta Cos | Plan Operation (days) | Actual Operation (days) | AFE Plan Budget | Total Actual Cost | TIME | COST
|  |  | KSB-065 | -13.15 | -309558.5817 | 21.1 | 34.25 | 2851130 | 3160688.5817 | 1.6232 | 1.1086
|  |  | P-460 | -0.81333 | 438356.8072 | 21.77 | 22.5833 | 2318089 | 1879732.1928 | 1.0374 | 0.8109
|  |  | P-461 | 0.058333 | 232659.6447 | 17.1 | 17.0417 | 2557831.42 | 2325171.7753 | 0.99659 | 0.90904
|  |  | P-462 | -3.7883 | 399420.7243 | 18.92 | 22.7083 | 2766044.56 | 2366623.8357 | 1.2002 | 0.8556
|  |  | P-463 | -3.15 | -259254.1459 | 17.1 | 20.25 | 2213895 | 2473149.1459 | 1.1842 | 1.1171
|  |  | P-464 | 1.2917 | 352693.2133 | 22.5 | 21.2083 | 2489280 | 2136586.7867 | 0.94259 | 0.85832
|  |  | P-466 | 0.64167 | -13556.6241 | 17.1 | 16.4583 | 2254026 | 2267582.6241 | 0.96248 | 1.006
|  |  | Ideal | [6 empty] | 0 | 0
[10 empty] | 100 | 100

## NPT Data
Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi | Jangan Diisi
No. | KKKS | Wilayah Kerja | Asset | Field | Nama Lokasi | C/F, C/O, New | Jenis Pekerjaan | Kategori Sumur | Tipe Sumur | Nama Rig | Tipe Rig | HP Rig | Plan and Budget | 2g - Well Control Operations / Situation | 2h - Lossing Circulation / Pumping LCM / Monitor Unplanned | 2j - Stuck Pipe Include Handling Operations | 3b - Washing / Reaming / Backreaming Unplanned | 5c - Circulate / Condition Mud Unplanned | 8a - Repair Power System | 8b - Repair Hoisting System | 8c - Repair Circulating System | 8d - Repair Rotating System | 8e - Repair Blow Out Preventer System | 8f - Tubular Problem | 8g - Personal Problem | 8n - Repair Safety System | 8s - Repair Others | 11d - Wireline / Slick Line Job Unplanned | 12f - Run Casing / Liner Problem | 18b - Squeeze Unplanned | 19a - Fishing Operations | 21a - Directional Services | 21b - Mud Services | 21c - MLU Services | 21d - UBD, MPD, Aerated Services | 21e - Casing Drilling Services | 21f - Cementing Services | 21g - Down Hole & Surface Services | 21h - Coiled Tubing Services | 21i - Wireline Services | 21j - Slick Line Services | 21k - RTO Services | 21l - Tubular Services | 21m - Well Head & X-Mastree Services | 21n - Solid Control Services | 21o - Waste Management Services | 21p - H2S Services | 21q - Stimulation Services | 21r - Marine Support Services | 21s - Transportation Services | 21t - Others Services | 22a - Material Problems | 22b - Social Issue | 22c - Environment Issue | 22d - Location Problems | 22e - Logistics Problems | 22f - Regulatory Problems | 22g - Other Problem Time | 23a - Waiting on Weather | 26d - Trip Problem Time | 28b - Swabbing Problem Time | 30c - Tree Problem Time | 31b - Other Completions Problem Time | Total NPT (hours) | PT Total (hours) | Total Time (hours) | Remark
1 | P | Indonesia | Zone F | J | J1 | C/F | New Well | Development | Directional | P#42.3 | Rig Darat | 1000 | 2022-06-22 | [50 empty] | 0 | 0
2 | P | Indonesia | Zone F | J | J2 | C/F | New Well | Development | Vertical | N#1 | Rig Darat | 550 | 2022-02-15 | [23 empty] | 8 | [26 empty] | 8 | 620 | 628
3 | P | Indonesia | Zone F | J | J3 | C/F | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2022-09-02 | [50 empty] | 0 | 0
4 | P | Indonesia | Zone F | J | J4 | New | New Well | Development | Vertical | N#1 | Rig Darat | 550 | 2022-07-15 | [50 empty] | 0 | 466 | 466
5 | P | Indonesia | Zone F | R | R1 | New | New Well | Development | Directional | T#12 | Rig Darat | 550 | 2022-05-15 | [50 empty] | 0 | 0
6 | P | Indonesia | Zone F | R | R2 | New | New Well | Development | Directional | T#12 | Rig Darat | 550 | 2022-04-02 | [5 empty] | 2 |  | 66.5 | 14.5 | 13 | [40 empty] | 96 | 726 | 822
7 | P | Indonesia | Zone F | R | R3 | New | New Well | Development | Vertical | T#12 | Rig Darat | 550 | 2022-07-02 | [5 empty] | 23 | [6 empty] | 3 | [31 empty] | 1 | 1 |  |  |  |  | 28 | 517 | 545
8 | P | Indonesia | Zone F | R | R4 | New | New Well | Development | Vertical | T#12 | Rig Darat | 550 | 2022-10-02 | [50 empty] | 0 | 0
9 | P | Indonesia | Zone F | R | R5 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-08-02 | [23 empty] | 3 | [23 empty] | 20.5 |  |  | 23.5 | 485.5 | 509
10 | P | Indonesia | Zone F | R | R6 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-11-15 | [50 empty] | 0 | 0
11 | P | Indonesia | Zone F | R | R7 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-09-15 | [50 empty] | 0 | 0
12 | P | Indonesia | Zone F | R | R8 | C/F | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-01-02 | [5 empty] | 36.5 | [7 empty] | 11 | [36 empty] | 47.5 | 492.5 | 540
13 | P | Indonesia | Zone F | R | R9 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-08-15 | [50 empty] | 0 | 0
14 | P | Indonesia | Zone F | R | R10 | New | New Well | Development | Vertical | T#12 | Rig Darat | 550 | 2022-11-02 | 144 | 14 | [5 empty] | 21.5 | [8 empty] | 52 | 38 | [29 empty] | 8 |  |  | 277.5 | 724.5 | 1002
15 | P | Indonesia | Zone F | R | R11 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-03-15 | [50 empty] | 0 | 409 | 409
16 | P | Indonesia | Zone F | R | R12 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-05-02 | [50 empty] | 0 | 486 | 486
17 | P | Indonesia | Zone F | R | R13 | New | New Well | Development | Vertical | P#23.1 | Rig Darat | 400 | 2022-06-15 | [45 empty] | 2 |  |  |  |  | 2 | 393 | 395
18 | P | Indonesia | Zone F | PS | PS1 | C/F | New Well | Development | Directional | P#41.3 | Rig Darat | 1000 | 2022-11-15 | [50 empty] | 0 | 0
19 | P | Indonesia | Zone F | J | J5 | New | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2022-02-08 | [26 empty] | 4 | [23 empty] | 4 | 530 | 534
20 | P | Indonesia | Zone F | J | J6 | C/O | New Well | Development | Directional | P#42.3 | Rig Darat | 1500 | 2022-05-02 | [50 empty] | 0 | 0
21 | P | Indonesia | Zone F | J | J7 | New | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2022-03-22 | [7 empty] | 13.5 | [10 empty] | 20 | [11 empty] | 21 | [19 empty] | 54.5 | 722.5 | 777
22 | P | Indonesia | Zone F | J | J8 | New | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2022-06-08 | [26 empty] | 21.5 | [23 empty] | 21.5 | 501.5 | 523
23 | P | Indonesia | Zone F | J | J9 | New | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2022-07-22 | [8 empty] | 5 | [35 empty] | 11 | [5 empty] | 16 | 730 | 746
24 | P | Indonesia | Zone F | J | J10 | New | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2022-09-08 | [50 empty] | 0 | 0
25 | P | Indonesia | Zone F | J | J11 | C/O | New Well | Development | Vertical | N#1 | Rig Darat | 550 | 2021-12-22 | [7 empty] | 40 | 13.5 |  | 18.5 | [39 empty] | 72 | 714 | 786
26 | P | Indonesia | Zone F | J | J12 | C/O | New Well | Development | Directional | P#17 | Rig Darat | 550 | 2021-12-01 | [50 empty] | 0 | 458 | 458
27 | P | Indonesia | Zone F | J | J13 | New | New Well | Development | Directional | N#1 | Rig Darat | 550 | 0 | [6 empty] | 31 | 12.5 | 33.5 | [8 empty] | 18 | [32 empty] | 95 | 709 | 804
28 | P | Indonesia | Zone F | J | J14 | C/O | New Well | Exploration | Directional | T#5 | Rig Darat | 700 | 2021-11-15 | [9 empty] | 18 | [14 empty] | 140 |  | 1.5 | [23 empty] | 159.5 | 1296.5 | 1456
29 | P | Indonesia | Zone F | PB | PB1 | C/O | New Well | Exploration | Vertical | P#41.3 | Rig Darat | 1500 | 2021-04-02 |  | 1625.5 | 113.5 |  |  | 7.5 | 83.5 |  | 11 | 145.5 | 48 |  |  |  |  | 3.5 | 188.5 | 342 | 51.5 |  |  | 3.5 |  | 13 | 387.5 |  | 5.5 | 1.5 |  |  | 14 |  | 15.5 | [11 empty] | 662 | [5 empty] | 3722.5 | 6635.5 | 10358
30 | P | Indonesia | Zone F | J | J15 | C/F | New Well | Exploration | Directional | P#42.3 | Rig Darat | 1500 | 2022-02-02 | 583.5 |  | 455.5 | 2 |  |  |  | 12 | 3 | 31.5 |  |  |  |  | 24 | 52 |  | 206 | 4 |  |  | 14.5 |  | 162 | 8.5 |  | 11.5 | [10 empty] | 4.5 |  |  |  |  | 25 |  | 202.5 | [5 empty] | 1802 | 2607 | 4409
Formulas:
Jangan Diisi = MainData[[#This Row],[WP&B 2022]]

## Graph NPT (hidden)
Asset | (All)
Field | (All)
Kategori Sumur | Development
Tipe Sumur | (All)
Nama Rig | (All)
Row Labels | Sum of Total NPT (hours) | Sum of PT Total (hours)
0 | 0 | 0
Grand Total | 0 | 0

## NPT Data Edit
Nama Sumur | Nama Rig | Category | Code | Duration | Consorsium | Specification | Remark
J2 | N#1 | NPT | 21f - Cementing Services | 8 | CL | Cement Unit | Repair compressor cementing unit
J2 | N#1 | PT |  | 620
R3 | T#12 | NPT | 8a - Repair Power System | 23 | T | Rig | Swab engine rig not working properly, gas trotel broken
R3 | T#12 | NPT | 8n - Repair Safety System | 3 | T | Rig | Overheat crane and dais rotary slip DC not working properly
R3 | T#12 | NPT | 22g - Other Problem Time | 1 | PI | Generator Set | Diesel engines are unable to withstand power loads
R3 | T#12 | NPT | 23a - Waiting on Weather | 1 |  |  | Heavy rain and lighting
R3 | T#12 | PT |  | 518
R8 | P#23.1 | NPT | 8a - Repair Power System | 36.5 | P | Rig | Drawwork transmission is leaked
R8 | P#23.1 | NPT | 8s - Repair Others | 11 | P | Rig | Seal and liner wash pipe on swivel are leaked
R8 | P#23.1 | PT |  | 492.5
R11 | P#23.1 | PT |  | 409
R12 | P#23.1 | PT |  | 486
J5 | P#17 | NPT | 21i - Wireline Services | 4 | Hal | Wireline Unit | Lost communication (error) on RDT sensor
J5 | P#17 | PT |  | 530
J7 | P#17 | NPT | 8c - Repair Circulating System | 13.5 | CL | Coiled Tubing Unit | Repair sensor indicator CTU
J7 | P#17 | NPT | 21a - Directional Services | 20 | P | Directional Drilling Unit | Drilling paramater abnormal condition (normal 612 gpm / 1330 psi), pressure drop 300 psi
J7 | P#17 | NPT | 21m - Well Head & X-Mastree Services | 21 | AM | Well Head & X-Mastree Unit | Casing Hanger 7" can not sit on CHS
J7 | P#17 | PT |  | 722.5
J8 | P#17 | NPT | 21i - Wireline Services | 21.5 | El | Wireline Unit | Detonator explodes, but primacord and shaped charge do not explode (low order detonating)
J8 | P#17 | PT |  | 501.5
J11 | N#1 | NPT | 8c - Repair Circulating System | 40 | N | Rig | Mud pump problems
J11 | N#1 | NPT | 8d - Repair Rotating System | 13.5 | N | Rig | Repair robotic system in TDS and the 1/4" hose in the grabber broken
J11 | N#1 | NPT | 8f - Tubular Problem | 18.5 | N | Rig | Indication of plug nozzles on the bit
J11 | N#1 | PT |  | 714
J12 | P#17 | PT |  | 458
J13 | N#1 | NPT | 8b - Repair Hoisting System | 31 | N | Rig | Swivel sinker bar disconnected
J13 | N#1 | NPT | 8c - Repair Circulating System | 12.5 | N | Rig | Change rubber piston on mud pump
J13 | N#1 | NPT | 8d - Repair Rotating System | 33.5 | N | Rig | TDS's motor liner leaked
J13 | N#1 | NPT | 19a - Fishing Operations | 18 | N | Rig | Fishing Job on debris of Milling Job
J13 | N#1 | PT |  | 709
J14 | T#5 | NPT | 8e - Repair Blow Out Preventer System | 18 | T | Rig | BOP leaked
J14 | T#5 | NPT | 21g - Down Hole & Surface Services | 131 | BS | Drill Stem Test Unit | Downhole valve broken, hydraulic engine & radiator leaked, annulus communication to DST#1
J14 | T#5 | NPT | 21g - Down Hole & Surface Services | 9 | CL | Coiled Tubing Unit | Coiled tubing disconnected
J14 | T#5 | NPT | 21i - Wireline Services | 1.5 | SN | Wireline Unit | Transmitter DSI tool not working properly
J14 | T#5 | PT |  | 1314.5
R2 | T#12 | NPT | 8a - Repair Power System | 2 | T | Rig | Break out tong leaking during break out conn stab dan float sub
R2 | T#12 | NPT | 8c - Repair Circulating System | 66.5 | T | Rig | Mud pump leaked
R2 | T#12 | NPT | 8d - Repair Rotating System | 14.5 | T | Rig | Top drive torque problem
R2 | T#12 | NPT | 8e - Repair Blow Out Preventer System | 13 | T | Rig | HCR 4“ connection, Bell Nipple and Annular connection, flexible hose to HCR 4-1/16"-5K psi and master valve BPM connection leaked
R2 | T#12 | PT |  | 726
R5 | P#23.1 | NPT | 21f - Cementing Services | 3 | CL | Cement Unit | Clamp pitolik 5" detached from connection
R5 | P#23.1 | NPT | 28b - Swabbing Problem Time | 20.5 | Hal | Wireline Unit | Sling disconnected during swabbing
R5 | P#23.1 | PT |  | 485.5
PB1 | P#41.3 | NPT | 2h - Lossing Circulation / Pumping LCM / Monitor Unplanned | 1625.5 |  |  | Loss circulation during drilling formation, combating loss
PB1 | P#41.3 | NPT | 2j - Stuck Pipe Include Handling Operations | 113.5 |  |  | Continue to RIH PDC 8-1/4" + BHA DD series from a depth of 2787 m to 2838 m while reamdown, string stucked (indication pack off)
PB1 | P#41.3 | NPT | 8a - Repair Power System | 7.5 | P | Rig | Repair and voltage checking of the Cat-3512 Generator Engine
PB1 | P#41.3 | NPT | 8b - Repair Hoisting System | 83.5 | P | Rig | Travelling block sags. Leakage in airflex low gear drawwork. Drawwork brake system lock, found control panel wichita brake drop pressure. Leakage in drawwork weight indicator. Travelling block can't go down. Troubleshooting the problem of lack of supply pressure HPU to Brake Drawork
PB1 | P#41.3 | NPT | 8d - Repair Rotating System | 11 | P | Rig | Top Connection Washpipe TDS leaked. Repair of Lube Pump Gearbox
PB1 | P#41.3 | NPT | 8e - Repair Blow Out Preventer System | 145.5 | P | Rig | Bonnet seal double ram leak during the BOP function test group 20-3/4" X 3000 psi. Leak in the 4" Co-flex and flange connection. Replacement RAM Shaft Double RAM and Replacement Annular BOP 13-5/8". Hydraulic impact wrenc lock malfunction. Replacing of a pair of variable ram segments. RBOP Function and Pressure Test. Tester plug stuck in annular
PB1 | P#41.3 | NPT | 8f - Tubular Problem | 48 | P | Rig | There is a reduction in OD from a 5" DP which breaks up to 4-3/4". Repair 5" DP slip
PB1 | P#41.3 | NPT | 12f - Run Casing / Liner Problem | 3.5 | Car | Casing Drive System | Casing stuck in power tong casing
PB1 | P#41.3 | NPT | 18b - Squeeze Unplanned | 188.5 |  |  | LOT remedial squeeze cementing. Carbonat Cement Plug Job for wellbore strengthening
PB1 | P#41.3 | NPT | 19a - Fishing Operations | 342 |  |  | Fishing with a 6x stand, free it with Jar Up
PB1 | P#41.3 | NPT | 21a - Directional Services | 51.5 | Schberg | Directional Drilling Unit | Directional tools problem (transmission from power section to bearing failed). Troubleshoot Schberg depth sensor switching and re-logging. Replace Mud Motor not working properly. Replacement of RCD bearings
PB1 | P#41.3 | NPT | 21d - UBD, MPD, Aerated Services | 3.5 | AD | RCD & MPD Unit | Leaks in Finger-Print MPD (leaks in the MP#4 liner and RCD bearings)
PB1 | P#41.3 | NPT | 21f - Cementing Services | 13 | Bak | Cement Unit | Repair cementing unit (loss prime in morris pump) and surge tank problem. Reverse out with rig pump to remove water ahead and spacer to CF
PB1 | P#41.3 | NPT | 21g - Down Hole & Surface Services | 387.5 | Sagatrade Murni | Liner Hanger, DSCC, ECP Unit | DSCC port cannot close. Junk screen Running Tool bolt comes off. Dressing tie-back. Junk screen bolt Running Tool detached & dressing tie-back. There is a leak in the EMR ADpter
PB1 | P#41.3 | NPT | 21i - Wireline Services | 5.5 | Schberg | Wireline Unit | The 18/32" nozzle on the bullnose is washouted. When OH logging 12", Run#5: XL Rock/Back Up MSCT, the coring motor cannot extend when going to coring point #1 @2017 m
PB1 | P#41.3 | NPT | 21j - Slick Line Services | 1.5 | Schberg | Wireline Unit | Indication of error in PSCC VSP
PB1 | P#41.3 | NPT | 21m - Well Head & X-Mastree Services | 14 |  |  | OD casing cannot fit into the wellhead
PB1 | P#41.3 | NPT | 21o - Waste Management Services | 15.5 | P | Rig | Cutting Auger sealed by cuttings
PB1 | P#41.3 | NPT | 22g - Other Problem Time | 662 |  |  | Stop operations, personnel at the location is Positive Covid-19.
PB1 | P#41.3 | PT |  | 6635.5
J4 | N#1 | PT |  | 466
J9 | P#17 | NPT | 8d - Repair Rotating System | 5 | P | Rig | Brake system malfunction, unable to released
J9 | P#17 | NPT | 22g - Other Problem Time | 11 | Wes | ESP Unit | Install power supply cable
J9 | P#17 | PT |  | 730
R13 | P#23.1 | NPT | 23a - Waiting on Weather | 2 |  |  | Can't load gun because of rain
R13 | P#23.1 | PT |  | 393
J15 | P#42.3 | NPT | 2g - Well Control Operations / Situation | 583.5 |  |  | During drilling the vertical traject 12-1/4" at a depth of 6250 ft, there was an increase in flow return from 25% to 40%. After the flow check is carried out there is a flow from the well.
J15 | P#42.3 | NPT | 2j - Stuck Pipe Include Handling Operations | 455.5 |  |  | After casing pressure 0 psi, the drilling string is tried to be lifted but the pipe is pinched.
J15 | P#42.3 | NPT | 3b - Washing / Reaming / Backreaming Unplanned | 2 |  |  | Casing collapse
J15 | P#42.3 | NPT | 8c - Repair Circulating System | 12 | P | Rig | Repair Mud Pump
J15 | P#42.3 | NPT | 8d - Repair Rotating System | 3 | P | Rig | Sub saver is detached
J15 | P#42.3 | NPT | 8e - Repair Blow Out Preventer System | 31.5 | P | Rig | Repair flange leak between Top Flange Annular and RCD Assy bottom connection
J15 | P#42.3 | NPT | 11d - Wireline / Slick Line Job Unplanned | 24 | Bak | Wireline Unit | RCI-Sampling tool Wireline baker short connection, RCI is squeezed at a depth of 6366 ftWL, RCI is squeezed at a depth of 6519 ftWL
J15 | P#42.3 | NPT | 12f - Run Casing / Liner Problem | 52 |  |  | 7" Liner Casing is seated at 6966 ft
J15 | P#42.3 | NPT | 19a - Fishing Operations | 206 |  |  | Fishing job
J15 | P#42.3 | NPT | 21a - Directional Services | 4 | P | Directional Drilling Unit | MWD Surface Aquicision problem, first PBL function test #1 PBL valve can open but cannot close
J15 | P#42.3 | NPT | 21d - UBD, MPD, Aerated Services | 14.5 | AFGL | RCD & MPD Unit | There was a flange leak between Top Annular and RCD Assy
J15 | P#42.3 | NPT | 21f - Cementing Services | 162 | Hal | Cement Unit | Cement premature set when cementing the casing 9-5/8"
J15 | P#42.3 | NPT | 21g - Down Hole & Surface Services | 8.5
J15 | P#42.3 | NPT | 21i - Wireline Services | 11.5 | Bak | Wireline Unit | Lock screw in baker wireline radioactive tools is not suitable, RCI-Sampling tool Wireline baker short connection
J15 | P#42.3 | NPT | 21t - Others Services | 4.5 | Sus | Fishing Unit | Found Ovsershot Bowl Top Body uneven/eccentric
J15 | P#42.3 | NPT | 22e - Logistics Problems | 25 | IM | Coordinator | Wait for the picking up of explosives
J15 | P#42.3 | NPT | 22g - Other Problem Time | 202.5 |  |  | 7" ID Liner is asymmetrical
J15 | P#42.3 | PT |  | 2607
R10 | T#12 | NPT | 2g - Well Control Operations / Situation | 144 |  |  | Water influx from nearby injection wells
R10 | T#12 | NPT | 2h - Lossing Circulation / Pumping LCM / Monitor Unplanned | 14 |  |  | Loss of circulation during injectivity test
R10 | T#12 | NPT | 8c - Repair Circulating System | 21.5 | T | Rig | Drawwork components (bearing) broken
R10 | T#12 | NPT | 18b - Squeeze Unplanned | 52 |  |  | Remedial squeeze cementing 7" casing due to loss of circulation
R10 | T#12 | NPT | 19a - Fishing Operations | 38 | T | Rig | DC Dies Slip components broken
R10 | T#12 | NPT | 28b - Swabbing Problem Time | 8 | T | Rig | Swab Job equIMent (sandline tool) that is not ready, the sinker bar cannot enter the lubricator
R10 | T#12 | PT |  | 724.5

## Data Rig (hidden)
Row Labels | Sum of Actual - Move (days) | Sum of Actual - R/U Endurance (days) | Sum of Actual - Operation (days) | Sum of Actual - R/D (days) | Rig Name | Actual - Move (days) | Actual - R/U Endurance (days) | Actual - Operation w/ NPT (days) | Actual - R/D (days) | Standby (days) | NPT (days) | Total Gross (days) | Rig Availability (days) | Rig Utility (days) | Average Rig Availability | Average Rig Utility | Actual - Operation (days)
NREM #01 | 17.75 | 70.7917 | 111.8333 | 8.8333 | NREM #01 | 17.75 | 70.7917 | 111.8333 | 8.8333 | #REF! | 7.2917 | #REF! | #REF! | 201.9167 | #REF! | #REF! | 104.5417
PDSI #17.2/NT45-M | 25 | 41.9583 | 126.5833 | 15 | PDSI #17.2/NT45-M | 25 | 41.9583 | 126.5833 | 15 | #REF! | 4 | #REF! | #REF! | 204.5417 | #REF! | #REF! | 122.5833
PDSI #23.1/CWKT210-M | 13.6667 | 47.8333 | 97.5417 | 10 | PDSI #23.1/CWKT210-M | 13.6667 | 47.8333 | 97.5417 | 10 | #REF! | 3.0417 | #REF! | #REF! | 166 | #REF! | #REF! | 94.5
PDSI #41.3/N110UE | 29 | 10 | 429.8333 | 3 | PDSI #41.3/N110UE | 29 | 10 | 429.8333 | 3 | #REF! | 155.1042 | #REF! | #REF! | 316.7292 | #REF! | #REF! | 274.7292
PDSI #42.3/N1500-E | 0 | 0 | 184.25 | 0 | PDSI #42.3/N1500-E | 0 | 0 | 184.25 | 0 | #REF! | 75.0833 | #REF! | #REF! | 109.1667 | #REF! | #REF! | 109.1667
TMMJ-05 | 17 | 0 | 60.6667 | 3.0417 | TMMJ-05 | 17 | 0 | 60.6667 | 3.0417 | #REF! | 6.6458 | #REF! | #REF! | 74.0625 | #REF! | #REF! | 54.0208
TMMJ-12 | 58.6667 | 12.125 | 98.7083 | 6 | TMMJ-12 | 58.6667 | 12.125 | 98.7083 | 6 | #REF! | 16.7292 | #REF! | #REF! | 158.7708 | #REF! | #REF! | 81.9792
Grand Total | 161.0833 | 182.7083 | 1109.4167 | 45.875
Row Labels | Sum of Total NPT (hours) | Sum of PT Total (hours) |  |  | Row Labels | Sum of Availability | Sum of Utility | Sum of Average Rig Availability | Sum of Average Rig Utility | [5 empty] | Row Labels | Sum of Actual - Move | Sum of Actual - R/U Endurance | Sum of Actual - Operation | Sum of Actual - R/D | Sum of Actual - NPT | Sum of Actual - Standby
NREM #01 | 175 | 2509 |  |  | NREM #01 | 97.23% | 76.77% | 100.2% | -0.6934% | [5 empty] | NREM #01 | 6.749% | 26.92% | 39.75% | 3.359% | 2.772% | 20.45%
PDSI #17.2/NT45-M | 96 | 2942 |  |  | PDSI #17.2/NT45-M | 100% | -0.2289% | 100.2% | -0.6934% | [5 empty] | PDSI #17.2/NT45-M | -0.02798% | -0.04695% | -0.1372% | -0.01679% | -0.004476% | 100.2%
PDSI #23.1/CWKT210-M | 73 | 2266 |  |  | PDSI #23.1/CWKT210-M | 100% | -0.1857% | 100.2% | -0.6934% | [5 empty] | PDSI #23.1/CWKT210-M | -0.01529% | -0.05351% | -0.1057% | -0.01119% | -0.003403% | 100.2%
PDSI #41.3/N110UE | 3722.5 | 6635.5 |  |  | PDSI #41.3/N110UE | 67.23% | 66.93% | 100.2% | -0.6934% | [5 empty] | PDSI #41.3/N110UE | 6.128% | 2.113% | 58.05% | 0.6339% | 32.77% | 0.2993%
PDSI #42.3/N1500-E | 1802 | 2607 |  |  | TMMJ-05 | 91.77% | 91.77% | 100.2% | -0.6934% | [5 empty] | PDSI #42.3/N1500-E | 0% | 0% | 59.25% | 0% | 40.75% | 0%
TMMJ-05 | 159.5 | 1296.5 |  |  | TMMJ-12 | 90.94% | 85.94% | 100.2% | -0.6934% | [5 empty] | TMMJ-05 | 21.06% | 0% | 66.93% | 3.769% | 8.234% | 0%
TMMJ-12 | 401.5 | 1967.5 |  |  | Grand Total | 100.1% | -0.6312% | 600.9% | -4.16% | [5 empty] | TMMJ-12 | 31.75% | 6.563% | 44.37% | 3.248% | 9.055% | 5.007%
Grand Total | 6429.5 | 20223.5 | [12 empty] | Grand Total | -0.09072% | -0.1029% | -0.4739% | -0.02584% | -0.1509% | 100.8%

## Graph NPT Edit (hidden)
Asset | Zona 1
Field | (All)
Kategori Sumur | Development
Nama Rig | (All)
Nama Sumur | (Multiple Items)
Row Labels | Sum of Duration
Grand Total

## Graph NPT Detail (hidden)
Asset | Zona 1
Field | (All)
Kategori Sumur | Development
Nama Rig | (All)
Category | NPT
Nama Sumur | (Multiple Items)
Row Labels | Sum of Duration
Grand Total

## Graph NPT Detail Well (hidden)
Asset | Zona 1
Field | (All)
Kategori Sumur | Development
Nama Rig | (All)
Category | NPT
Sum of Duration | Column Labels
Row Labels | Grand Total
Grand Total

## Graph NPT Clustered Column (hidden)
Asset | Zona 1
Field | (All)
Kategori Sumur | Development
Nama Rig | (All)
Category | NPT
Sum of Duration | Column Labels
Row Labels | Grand Total
Grand Total

## Cost Data Edit
Nama Sumur | C/F, C/O, New | Nama Rig | Tipe Rig | HP Rig | WP&B 2022 | Cost Category | Value
J2 | C/F | N#1 | Rig Darat | 550 | 2022-02-15 | Budget | 2868237
J2 | C/F | N#1 | Rig Darat | 550 | 2022-02-15 | Additional | -467911.7862
J2 | C/F | N#1 | Rig Darat | 550 | 2022-02-15 | DHB | 1485151.9541
J2 | C/F | N#1 | Rig Darat | 550 | 2022-02-15 | CHB | 915173.2597
J2 | C/F | N#1 | Rig Darat | 550 | 2022-02-15 | NPT Impact | 5346.94
J4 | New | N#1 | Rig Darat | 550 | 2022-07-15 | Budget | 2692554
J4 | New | N#1 | Rig Darat | 550 | 2022-07-15 | Additional | -628087.1455
J4 | New | N#1 | Rig Darat | 550 | 2022-07-15 | DHB | 1281085.9424
J4 | New | N#1 | Rig Darat | 550 | 2022-07-15 | CHB | 783380.9122
R2 | New | T#12 | Rig Darat | 550 | 2022-04-02 | Budget | 2851130
R2 | New | T#12 | Rig Darat | 550 | 2022-04-02 | Additional | 309558.5817
R2 | New | T#12 | Rig Darat | 550 | 2022-04-02 | DHB | 2084781.7294
R2 | New | T#12 | Rig Darat | 550 | 2022-04-02 | CHB | 1075906.8523
R2 | New | T#12 | Rig Darat | 550 | 2022-04-02 | NPT Impact | 175800.31
R3 | New | T#12 | Rig Darat | 550 | 2022-07-02 | Budget | 2766044.56
R3 | New | T#12 | Rig Darat | 550 | 2022-07-02 | Additional | -399420.7243
R3 | New | T#12 | Rig Darat | 550 | 2022-07-02 | DHB | 1630790.9985
R3 | New | T#12 | Rig Darat | 550 | 2022-07-02 | CHB | 735832.8372
R3 | New | T#12 | Rig Darat | 550 | 2022-07-02 | NPT Impact | 16230.1
R5 | New | P#23.1 | Rig Darat | 400 | 2022-08-02 | Budget | 2489280
R5 | New | P#23.1 | Rig Darat | 400 | 2022-08-02 | Additional | -352693.2133
R5 | New | P#23.1 | Rig Darat | 400 | 2022-08-02 | DHB | 1166626.3932
R5 | New | P#23.1 | Rig Darat | 400 | 2022-08-02 | CHB | 969960.3935
R5 | New | P#23.1 | Rig Darat | 400 | 2022-08-02 | NPT Impact | 46752.1
R8 | C/F | P#23.1 | Rig Darat | 400 | 2022-01-02 | Budget | 2318089
R8 | C/F | P#23.1 | Rig Darat | 400 | 2022-01-02 | Additional | -438356.8072
R8 | C/F | P#23.1 | Rig Darat | 400 | 2022-01-02 | DHB | 1225106.9856
R8 | C/F | P#23.1 | Rig Darat | 400 | 2022-01-02 | CHB | 654625.2072
R8 | C/F | P#23.1 | Rig Darat | 400 | 2022-01-02 | NPT Impact | 115750.84
R11 | New | P#23.1 | Rig Darat | 400 | 2022-03-15 | Budget | 2557831.42
R11 | New | P#23.1 | Rig Darat | 400 | 2022-03-15 | Additional | -232659.6447
R11 | New | P#23.1 | Rig Darat | 400 | 2022-03-15 | DHB | 1631787.4111
R11 | New | P#23.1 | Rig Darat | 400 | 2022-03-15 | CHB | 693384.3642
R12 | New | P#23.1 | Rig Darat | 400 | 2022-05-02 | Budget | 2213895
R12 | New | P#23.1 | Rig Darat | 400 | 2022-05-02 | Additional | 259254.1459
R12 | New | P#23.1 | Rig Darat | 400 | 2022-05-02 | DHB | 1652687.411
R12 | New | P#23.1 | Rig Darat | 400 | 2022-05-02 | CHB | 820461.735
R13 | New | P#23.1 | Rig Darat | 400 | 2022-06-15 | Budget | 2254026
R13 | New | P#23.1 | Rig Darat | 400 | 2022-06-15 | Additional | 13556.6241
R13 | New | P#23.1 | Rig Darat | 400 | 2022-06-15 | DHB | 1607042.1022
R13 | New | P#23.1 | Rig Darat | 400 | 2022-06-15 | CHB | 660540.522
R13 | New | P#23.1 | Rig Darat | 400 | 2022-06-15 | NPT Impact | 2027.06
J5 | New | P#17 | Rig Darat | 550 | 2022-02-08 | Budget | 3226593.01
J5 | New | P#17 | Rig Darat | 550 | 2022-02-08 | Additional | -686179.019
J5 | New | P#17 | Rig Darat | 550 | 2022-02-08 | DHB | 1622813.3722
J5 | New | P#17 | Rig Darat | 550 | 2022-02-08 | CHB | 917600.6188
J5 | New | P#17 | Rig Darat | 550 | 2022-02-08 | NPT Impact | 5316.84
J7 | New | P#17 | Rig Darat | 550 | 2022-03-22 | Budget | 2508579
J7 | New | P#17 | Rig Darat | 550 | 2022-03-22 | Additional | -252103.1299
J7 | New | P#17 | Rig Darat | 550 | 2022-03-22 | DHB | 1090648.2784
J7 | New | P#17 | Rig Darat | 550 | 2022-03-22 | CHB | 1165827.5916
J7 | New | P#17 | Rig Darat | 550 | 2022-03-22 | NPT Impact | 40925.059
J8 | New | P#17 | Rig Darat | 550 | 2022-06-08 | Budget | 2362404
J8 | New | P#17 | Rig Darat | 550 | 2022-06-08 | Additional | -288052.44
J8 | New | P#17 | Rig Darat | 550 | 2022-06-08 | DHB | 848047.6475
J8 | New | P#17 | Rig Darat | 550 | 2022-06-08 | CHB | 1226303.9124
J8 | New | P#17 | Rig Darat | 550 | 2022-06-08 | NPT Impact | 27887.13
J9 | New | P#17 | Rig Darat | 550 | 2022-07-22 | Budget | 2433487
J9 | New | P#17 | Rig Darat | 550 | 2022-07-22 | Additional | 52184.1526
J9 | New | P#17 | Rig Darat | 550 | 2022-07-22 | DHB | 1092510.742
J9 | New | P#17 | Rig Darat | 550 | 2022-07-22 | CHB | 1393160.4107
J9 | New | P#17 | Rig Darat | 550 | 2022-07-22 | NPT Impact | 13909.8
J11 | C/O | N#1 | Rig Darat | 550 | 2021-12-22 | Budget | 2623025.7528
J11 | C/O | N#1 | Rig Darat | 550 | 2021-12-22 | Additional | -195232.4839
J11 | C/O | N#1 | Rig Darat | 550 | 2021-12-22 | DHB | 1540219.1055
J11 | C/O | N#1 | Rig Darat | 550 | 2021-12-22 | CHB | 887574.1634
J11 | C/O | N#1 | Rig Darat | 550 | 2021-12-22 | NPT Impact | 73120.52
J12 | C/O | P#17 | Rig Darat | 550 | 2021-12-01 | Budget | 2529742
J12 | C/O | P#17 | Rig Darat | 550 | 2021-12-01 | Additional | -452420.4029
J12 | C/O | P#17 | Rig Darat | 550 | 2021-12-01 | DHB | 1262404.0252
J12 | C/O | P#17 | Rig Darat | 550 | 2021-12-01 | CHB | 814917.572
J13 | New | N#1 | Rig Darat | 550 |  | Budget | 2466748
J13 | New | N#1 | Rig Darat | 550 |  | Additional | -481077.0024
J13 | New | N#1 | Rig Darat | 550 |  | DHB | 973032.7108
J13 | New | N#1 | Rig Darat | 550 |  | CHB | 1012638.2867
J13 | New | N#1 | Rig Darat | 550 |  | NPT Impact | 67700
J14 | C/O | T#5 | Rig Darat | 700 | 2021-11-15 | Budget | 10193828
J14 | C/O | T#5 | Rig Darat | 700 | 2021-11-15 | Additional | -3012413.8674
J14 | C/O | T#5 | Rig Darat | 700 | 2021-11-15 | DHB | 4059872.0076
J14 | C/O | T#5 | Rig Darat | 700 | 2021-11-15 | CHB | 3121542.125
J14 | C/O | T#5 | Rig Darat | 700 | 2021-11-15 | NPT Impact | 453349.53
PB1 | C/O | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Budget | 26620003
PB1 | C/O | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Additional | 27266011.2041
PB1 | C/O | P#41.3 | Rig Darat | 1500 | 2021-04-02 | DHB | 47485213.662
PB1 | C/O | P#41.3 | Rig Darat | 1500 | 2021-04-02 | CHB | 6400800.542
PB1 | C/O | P#41.3 | Rig Darat | 1500 | 2021-04-02 | NPT Impact | 16637047.69
J15 | C/F | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Budget | 11423390.2688
J15 | C/F | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Additional | 10346686.6412
J15 | C/F | P#42.3 | Rig Darat | 1500 | 2022-02-02 | DHB | 8477924.5155
J15 | C/F | P#42.3 | Rig Darat | 1500 | 2022-02-02 | CHB | 13292152.3945
J15 | C/F | P#42.3 | Rig Darat | 1500 | 2022-02-02 | NPT Impact | 5119327.52
R10 | New | T#12 | Rig Darat | 550 | 2022-11-02 | Budget | 2505645
R10 | New | T#12 | Rig Darat | 550 | 2022-11-02 | Additional | -388052.9595
R10 | New | T#12 | Rig Darat | 550 | 2022-11-02 | DHB | 1568197.6731
R10 | New | T#12 | Rig Darat | 550 | 2022-11-02 | CHB | 1325500.2863
R10 | New | T#12 | Rig Darat | 550 | 2022-11-02 | NPT Impact | 630823.77

## Plan Actual Data Edit
Nama Sumur | C/F, C/O, New | Jenis Pekerjaan | Kategori Sumur | Tipe Sumur | Status Sumur | Nama Rig | Tipe Rig | HP Rig | WP&B 2022 | Category | Properties | Value
J2 | C/F | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-02-15 | Plan | DHB | 9.4167
J2 | C/F | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-02-15 | Plan | CHB | 10.8125
J2 | C/F | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-02-15 | Actual | DHB | 11
J2 | C/F | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-02-15 | Actual | CHB | 15.1667
J4 | New | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-07-15 | Plan | DHB | 8.3
J4 | New | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-07-15 | Plan | CHB | 11.4
J4 | New | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-07-15 | Actual | DHB | 9.1042
J4 | New | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-07-15 | Actual | CHB | 10.3125
R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | Plan | DHB | 11.23
R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | Plan | CHB | 9.92
R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | Actual | DHB | 21.7917
R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | Actual | CHB | 12.4583
R3 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-07-02 | Plan | DHB | 7.42
R3 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-07-02 | Plan | CHB | 11.5
R3 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-07-02 | Actual | DHB | 7.7083
R3 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-07-02 | Actual | CHB | 15
R5 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-08-02 | Plan | DHB | 9.25
R5 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-08-02 | Plan | CHB | 14.69
R5 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-08-02 | Actual | DHB | 7.5417
R5 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-08-02 | Actual | CHB | 13.6667
R8 | C/F | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-01-02 | Plan | DHB | 7.31
R8 | C/F | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-01-02 | Plan | CHB | 14.46
R8 | C/F | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-01-02 | Actual | DHB | 8.9167
R8 | C/F | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-01-02 | Actual | CHB | 13.6667
R11 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-03-15 | Plan | DHB | 7.97
R11 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-03-15 | Plan | CHB | 9.13
R11 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-03-15 | Actual | DHB | 7
R11 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-03-15 | Actual | CHB | 10.0417
R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | Plan | DHB | 7.97
R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | Plan | CHB | 9.13
R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | Actual | DHB | 7.4375
R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | Actual | CHB | 12.8125
R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | Plan | DHB | 8.23
R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | Plan | CHB | 10.04
R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | Actual | DHB | 7.2292
R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | Actual | CHB | 9.2292
J5 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-02-08 | Plan | DHB | 10.3333
J5 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-02-08 | Plan | CHB | 21.2292
J5 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-02-08 | Actual | DHB | 11.2917
J5 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-02-08 | Actual | CHB | 10.9583
J7 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-03-22 | Plan | DHB | 11.1
J7 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-03-22 | Plan | CHB | 18.1
J7 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-03-22 | Actual | DHB | 11.375
J7 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-03-22 | Actual | CHB | 21
J8 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-06-08 | Plan | DHB | 10.0208
J8 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-06-08 | Plan | CHB | 17.8125
J8 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-06-08 | Actual | DHB | 8.5417
J8 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-06-08 | Actual | CHB | 13.25
J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | Plan | DHB | 10.02
J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | Plan | CHB | 17.81
J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | Actual | DHB | 9.0417
J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | Actual | CHB | 22
J11 | C/O | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2021-12-22 | Plan | DHB | 11.4375
J11 | C/O | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2021-12-22 | Plan | CHB | 16.375
J11 | C/O | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2021-12-22 | Actual | DHB | 15.6458
J11 | C/O | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2021-12-22 | Actual | CHB | 17.1042
J12 | C/O | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2021-12-01 | Plan | DHB | 9.9
J12 | C/O | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2021-12-01 | Plan | CHB | 16.1
J12 | C/O | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2021-12-01 | Actual | DHB | 7.2292
J12 | C/O | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2021-12-01 | Actual | CHB | 11.8958
J13 | New | New Well | Development | Directional | Completed | N#1 | Rig Darat | 550 |  | Plan | DHB | 11.3
J13 | New | New Well | Development | Directional | Completed | N#1 | Rig Darat | 550 |  | Plan | CHB | 20.2
J13 | New | New Well | Development | Directional | Completed | N#1 | Rig Darat | 550 |  | Actual | DHB | 13.4167
J13 | New | New Well | Development | Directional | Completed | N#1 | Rig Darat | 550 |  | Actual | CHB | 20.0833
J14 | C/O | New Well | Exploration | Directional | Completed | T#5 | Rig Darat | 700 | 2021-11-15 | Plan | DHB | 24.92
J14 | C/O | New Well | Exploration | Directional | Completed | T#5 | Rig Darat | 700 | 2021-11-15 | Plan | CHB | 60.23
J14 | C/O | New Well | Exploration | Directional | Completed | T#5 | Rig Darat | 700 | 2021-11-15 | Actual | DHB | 22.1667
J14 | C/O | New Well | Exploration | Directional | Completed | T#5 | Rig Darat | 700 | 2021-11-15 | Actual | CHB | 38.5
PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Plan | DHB | 114.14
PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Plan | CHB | 99.69
PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Actual | DHB | 336.375
PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Actual | CHB | 93.4583
J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Plan | DHB | 12.5
J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Plan | CHB | 34.9
J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Actual | DHB | 88.8542
J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Actual | CHB | 95.3958
R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | Plan | DHB | 8.48
R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | Plan | CHB | 14.02
R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | Actual | DHB | 14.1667
R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | Actual | CHB | 27.5833

## Cost Effectivity
Nama Lokasi | C/F, C/O, New | Jenis Pekerjaan | Kategori Sumur | Tipe Sumur | Status Sumur | Nama Rig | Tipe Rig | HP Rig | WP&B 2022 | Category | Value
J2 | C/F | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-02-15 | Budget | 83.69%
J4 | New | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2022-07-15 | Budget | 76.67%
R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | Budget | 100%
R2 | New | New Well | Development | Directional | Completed | T#12 | Rig Darat | 550 | 2022-04-02 | Additional | 10.86%
R3 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-07-02 | Budget | 85.56%
R5 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-08-02 | Budget | 85.83%
R8 | C/F | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-01-02 | Budget | 81.09%
R11 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-03-15 | Budget | 90.9%
R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | Budget | 100%
R12 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-05-02 | Additional | 11.71%
R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | Budget | 100%
R13 | New | New Well | Development | Vertical | Completed | P#23.1 | Rig Darat | 400 | 2022-06-15 | Additional | 0.6014%
J5 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-02-08 | Budget | 78.73%
J7 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-03-22 | Budget | 89.95%
J8 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-06-08 | Budget | 87.81%
J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | Budget | 100%
J9 | New | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2022-07-22 | Additional | 2.144%
J11 | C/O | New Well | Development | Vertical | Completed | N#1 | Rig Darat | 550 | 2021-12-22 | Budget | 92.56%
J12 | C/O | New Well | Development | Directional | Completed | P#17 | Rig Darat | 550 | 2021-12-01 | Budget | 82.12%
J13 | New | New Well | Development | Directional | Completed | N#1 | Rig Darat | 550 |  | Budget | 80.5%
J14 | C/O | New Well | Exploration | Directional | Completed | T#5 | Rig Darat | 700 | 2021-11-15 | Budget | 70.45%
PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Budget | 100%
PB1 | C/O | New Well | Exploration | Vertical | Completed | P#41.3 | Rig Darat | 1500 | 2021-04-02 | Additional | 102.4%
J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Budget | 100%
J15 | C/F | New Well | Exploration | Directional | Completed | P#42.3 | Rig Darat | 1500 | 2022-02-02 | Additional | 90.57%
R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | Budget | 100%
R10 | New | New Well | Development | Vertical | Completed | T#12 | Rig Darat | 550 | 2022-11-02 | Additional | 15.49%